## Sheet1
Name: Ranadheer K	ID:MT2012060
DATE	Activity Name	Hours Spend		UC.Design	UC9.Design+UC10.Design
19/01/13	UC4.design	4		UC5	Notify buyer for order status
20/01/13	Nothing			UC6	Registration
21/01/13	UC5.design	2		UC7	View product by seller
22/01/13	Meeting.KVD	1		UC8	Update discount
23/01/13	Nothing
24/01/13	Nothing
25/01/13	Nothing
26/01/13	Nothing
27/01/13	Nothing
28/01/13	Nothing
29/01/13	UC5.design	3.5
30/01/13	Meeting.TA	4
31/01/13	Nothing
01/02/13	Nothing
02/02/13	Nothing
03/02/13	UC4.design	3

04/02/13	Mini Project	3
05/02/13	Nothing
06/02/13	Mini Project	5
07/02/13	Mini Project	3.5
08/02/13	Nothing
09/02/13	Meeting.KVD	2.5
10/02/13	Nothing
11/02/13	Nothing
12/02/13	Nothing
13/02/13	Mini Project	5
14/02/13	Nothing
15/02/13	Meeting.KVD	1.5
16/02/13	Nothing
17/02/13	Others	5
18/02/13	Meeting.TA	1.2
19/02/13	Nothing
20/02/13	Others	1.5
21/02/13	Nothing
22/02/13	Nothing
23/02/13	Nothing
24/02/13	Nothing
25/02/13	Nothing
26/02/13	Nothing
27/02/13	Nothing
28/02/13	Nothing
01/03/13	Nothing
02/03/13	Meeting.group	1
03/03/13	Nothing
04/03/13	Nothing
05/03/13	Nothing
06/03/13	Nothing
07/03/13	Nothing
08/03/13	Nothing
09/03/13	Nothing
10/03/13	Nothing
11/03/13	Nothing
12/03/13	Nothing
13/03/13	Meeting.group	0.5
14/03/13	UC.design	6
15/03/13	UC.design	5.5
16/03/13	Nothing
17/03/13	Nothing
18/03/13	UC.design	4
19/03/13	Mini Project	4
20/03/13	Nothing
21/03/13	Nothing
22/03/13	Nothing
23/03/13	UC1.Coding	4.5
24/03/13	UC.designDOC	5
25/03/13	Others	6
26/03/13	Nothing
27/03/13	Nothing
28/03/13	Nothing
29/03/13	Others	4
30/03/13	Nothing
31/03/13	UC1.Coding	6
01/04/13	UC1.Coding	3
02/04/13	UC1.Coding	3.5
03/04/13	uc.coding	4
04/04/13	Nothing
05/04/13	Nothing
06/04/13	UC.testing	4
07/04/13	UC5.coding	7
08/04/13	UC5.coding	6.5
09/04/13	UC6.coding	6
10/04/13	UC7.coding	3
11/04/13	Nothing
12/04/13	UC7.coding	7
13/04/13	UC7.integration	5
14/04/13	Integartion	8
14/04/13	Meeting.TA	2
15/04/13	UC.Integration	6
16/04/13	UC8.coding	7.5
17/04/13	uc.Testing	5
18/04/13	UC.Review	5.5
19/04/13	UC.testing	7
20/04/13
21/04/13
22/04/13
23/04/13
24/04/13
25/04/13
26/04/13
27/04/13
28/04/13
29/04/13
30/04/13
01/05/13
02/05/13
03/05/13
04/05/13
05/05/13
06/05/13
07/05/13
08/05/13
09/05/13
10/05/13
11/05/13
12/05/13
13/05/13
14/05/13
15/05/13
16/05/13
17/05/13
18/05/13
19/05/13
20/05/13
21/05/13
22/05/13
23/05/13
24/05/13
25/05/13
26/05/13
27/05/13
28/05/13
29/05/13
30/05/13
31/05/13